## Draft
Project Phase | Id | Task | Duration | Planned Start Date | Planned Completion Date | % Completed | Days Completed
Phase 1: Project Planning and Proposal | 1 | Phase 1: Project Planning and Proposal | 21 | 2023-08-21 | 2023-09-11 | 100% | 21
| 1.1 | Github/Trello setup | 7 | 2023-08-21 | 2023-08-28 | 100% | 7
| 1.2 | Project Proposal Preparation | 8 | 2023-08-29 | 2023-09-06 | 100% | 8
| 1.3 | Risk Management Plan | 1 | 2023-09-07 | 2023-09-08 | 100% | 1
| 1.4 | Presentation and Video Creation | 1 | 2023-09-09 | 2023-09-10 | 100% | 1
Phase 2: System Specifications and Requirements | 2 | Phase 2: System Specifications and Requirements | 20 | 2023-09-12 | 2023-10-02 | 0% | 0
| 2.1 | Requirement Analysis | 4 | 2023-09-12 | 2023-09-16 | 0% | 0
| 2.2 | Draft System Specifications | 4 | 2023-09-17 | 2023-09-21 | 0% | 0
| 2.3 | Review and Finalize Specifications | 9 | 2023-09-22 | 2023-10-01 | 0% | 0
Phase 3: Project Launch and Execution | 3 | Phase 3: Project Launch and Execution | 20 | 2023-10-03 | 2023-10-23 | 0% | 0
| 3.1 | Client Frontend and Backend Feature Implementation | 7 | 2023-10-03 | 2023-10-10 | 0% | 0
| 3.2 | Doctors /Clinic Official Frontend/Backend Implementation | 7 | 2023-10-11 | 2023-10-18 | 0% | 0
| 3.3 | Test/ Draft Report | 4 | 2023-10-19 | 2023-10-23 | 0% | 0
Phase 4: Project Execution | 4 | Phase 4: Project Execution | 20 | 2023-10-24 | 2023-11-13 | 0% | 0
| 4.1 | Appointment Scheduler Implementation | 5 | 2023-10-24 | 2023-10-29 | 0% | 0
| 4.2 | Appointment Tracking and Visualization | 5 | 2023-10-30 | 2023-11-04 | 0% | 0
| 4.3 | Web App Deployment | 4 | 2023-11-05 | 2023-11-09 | 0% | 0
| 4.4 | Test/Draft Report | 3 | 2023-11-10 | 2023-11-13 | 0% | 0
Phase 5: Project Testing & Deployment | 5 | Phase 5: Project Testing & Deployment | 20 | 2023-11-14 | 2023-12-04 | 0% | 0
| 5.1 | System Testing | 3 | 2023-11-14 | 2023-11-17 | 0% | 0
| 5.2 | Usability Testing | 4 | 2023-11-18 | 2023-11-22 | 0% | 0
| 5.3 | Deployment | 3 | 2023-11-23 | 2023-11-26 | 0% | 0
| 5.4 | Documentation and Project Report | 3 | 2023-11-27 | 2023-11-30 | 0% | 0
| 5.5 | Final Presentation | 3 | 2023-12-01 | 2023-12-04 | 0% | 0

## Sheet1
Id | Task | Duration | Planned Start Date | Planned Completion Date
` | Github/Trello setup | 5 | 2023-09-06 | 2023-09-11
1 | Deliverable 1 | 5 | 2023-09-06 | 2023-09-11
1.1 | Project Proposal
1.2 | Member lead
1.3 | Presentation
2 | Deliverable 2 | 20 | 2023-09-12 | 2023-10-02 | 45175
2.1 | Core Basic Functionality
2.2 | Client Frontend and Backend
2.3 | Doctors /Clinic Official Frontend/Backend
3 | Deliverable 3 | 20 | 2023-10-03 | 2023-10-23 | 45264
3.1 | Time Scheduler
3.2 | Appointment tracking and Visualization
4 | Deliverable 4 | 20 | 2023-10-24 | 2023-11-13
4.1 | Coding
4.2 | Web App Deployment
5 | Deliverable 5 | 20 | 2023-11-14 | 2023-12-04
5.1 | System Testing
5.2 | Usability Testing
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34

## Sheet2
| Project Start Date | 2023-08-21
[8 empty] | August |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
| Project Name | Book a doc/Med Voyage | [5 empty] | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18
# | Task | Assigned to | Start | End | Duration | Status | %Done
| Deliverable 1 |  | 2023-09-06 | 2023-09-11 | 5
| Deliverable 2 |  | 2023-09-12 | 2023-10-02 | 20
| Deliverable 3 |  | 2023-10-03 | 2023-10-23 | 20
| Deliverable 4 |  | 2023-10-24 | 2023-11-13 | 20
| Deliverable 5 |  | 2023-11-14 | 2023-12-04 | 20

## Recommendation1
Planned Completion Date | (All) | Planned Start Date
2023-09-06
2023-09-12
2023-10-03
2023-10-24
2023-11-14

## Recommendation2
Row Labels | Sum of Duration | Sum of Planned Start Date
1 | 5 | 2023-09-06
2 | 20 | 2023-09-12
3 | 20 | 2023-10-03
4 | 20 | 2023-10-24
5 | 20 | 2023-11-14
Grand Total | 85 | 226025